## Reference Stories
Reference Story No | Story Pool | Story Source | Summary: 25-50 Words | Word count, sort of
1 | 1 | EECS 168, common intro program | "Hello World!": Print "Hello World!" to show a baseline understanding of a new programming language. Typically only one or a few lines of code long, "simplest project." | 27
2 | 1 | EECS 168, Lab 8 | Developed a Python program to take a document and return a dictionary of unique words with word counts, filtering out special characters and capital letters. | 25
3 | 1 | EECS 268, Lab 4 | Created a Python function to recursively calculate the nth Fibonnacci Number, with f(0)=1, f(1)=1, and then f(n+1)=f(n)+f(n-1) for the rest of the numbers in the sequence. | 26
4 | 1 | EECS 330, Lab 11 | Implemented a Python Selection Sort function to take an array and sort it, in place, using Selection Sort to order the integer elements of the array from smallest to largest. | 30
5 | 2 | EECS 388, Lab 1 | Set up a github repository to upload the EECS388 Labs throughout the semester. Complete a set of instructions, SSH into the eecs lab machines if necessary, learn to commit messages, and run simple C programs. | 35
6 | 2 | EECS 678, Lab 0 | Run a simple C program, working with pointers, dynamic memory allocation, and manual memory management. Implement linked list strcture (e.g. create nodes) and detect cycles in linked lists. | 28
7 | 2 | EECS 168, Lab 1 (exercise 1) | Write a simple Python program that asks the user some simple questions and return a message based on user responses. Implement the logic given by professor. | 26
8 | 2 | EECS 168, Lab 1 (exercise 2) | Write a simple Python calculator that asks the user to enter a numerator and denominator. The program will print the division with answer and remainder, or an error message to prevent crashing. | 32
9 | 3 | EECS 168, Lab 6 (exercise 2) | Read an array from a file, then perform several different operations or modifications to that file data to be written into new files. E.g, one output file contains the original array but with the data in each column flipped from top to bottom. | 43
10 | 3 | EECS 268, Lab 9 | Simulate a hospital waiting room by implementing a max heap in python to create a prioity queue to determine the order patients should be treated in. | 26
11 | 3 | EECS 581, Project 1 Minesweeper | Uncover all mines on the board when the user clicks on a mine. Also, display a message informing the user that they have lost the minesweeper game. | 27
12 | 3 | EECS 348, Lab 7 | Create a simple website that contains text, images, and links to other sites; accepts user input to change text attributes; and generates a multiplication table based in a user inputted size. | 31
13 | 5 | EECS623, Roguelike Game | Implement a modular point-based health system for video-game enemies. Designed and integrated damage calculation to allow enemies to respond dynamically to player actions and status effects. Includes varying amounts of damage depending on enemy-specific weaknesses. | 35
14 | 5 | EECS581, Project 2 Maintenance | Develop Easy and Medium difficulty AI solvers for a Minesweeper game, where the Easy solver randomly selects unopened cells, while the the Medium solver applies the following logic: flags hidden cells when all neighbors are unknown, and safely reveals cells when all bombs are identified. | 45
15 | 5 | EECS268, Process Simulator | Build a node-based LinkedStack to model a process call stack: parsed START/CALL/RETURN/RAISE file-driven commands, model exception unwinding to handlers or main, and emit precise state/error messages. | 26
16 | 5 | EECS678, POSIX Signals | Implement signal-driven control flow in C by registering handlers for SIGIN and SIGTSTP, maintaining a SIGINT counter, and promprting to exit after five interrupts. Use built-in functions to enforce a 3-second timeout and clean program termination. | 36
17 | 8 | EECS 678 Process Scheduler Lab | This lab implemented a discrete event scheduler. This consisted of implementing a priority queue, a priority queue API, six scheduling algorithms, and several ancillary functions (in C). | 28
18 | 8 | EECS 447 Library Database Project | This project implemented a database management system for a simulated public library. It involved creating all data schema and dependencies, and creating the database and its functions. The implementation involved creating the schema and necessary SQL queries to fulfill all library requirements. | 42
19 | 8 | EECS 510 Finite State Machine Project | This project created and implemented a formal language. It included creating an alphabet, a grammar, a data structure, and designing and implementing a finite automaton representing the language. | 28
20 | 8 | EECS 268 Computer Scheduler Lab | This lab implemented a mock CPU scheduler. Implementation included creating node based queue and stack data structures, four process handling functions, and several ancillary functions. | 25
21 | 13 | EECS 678 Quash | Implement a Unix-like shell in C that supports creating processes, pipes, I/O redirection, background jobs, and built-in commands. Designed process management using fork (), execvp(), and waitpid(), which enables concurrent execution and environment variable handling | 36
22 | 13 | EECS 623 Rat Man | Reskinned Pac-Man with new mechanics and enemy AI. Programmed cat enemies with pathfinding and unique movement behaviors. Implemented a key-mash battle system triggered by power pellets. Integrated collisions, sound effects, tunnels, win/lost scenes | 33
23 | 13 | EECS 623 Item mechanics + map generation | Implemented randomized map generation along with dynamically placed vending machines and enemies. Designed item system of four consumables with unique stat effects, inventory mechanics + UI. Integrated adaptive background music and environmental feedback | 33
24 | 13 | EECS 623 Dialogue Battle + Animation | Developed game's intro animation and interactive dialogue-battle system, letting players choose persuasion or intimidation strategies against varied enemy classes. Implemented cooldown detection to prevent spamming during battles, unique enemy susceptibilities, collision. Combined narrative scripting for combat logic | 38

## Project Reference Brainstorm
Project/Project Part | Class
Minesweeper Project | EECS 581
Quash Project | EECS 678
Process Scheduler Lab | EECS 678
Hello World Lab | EECS 168
Database Project | EECS 447
Stack Implementation Lab | EECS 268
Arcade Shakeout | EECS 623
Roguelike Game | EECS 623

## Requirements Stack
Requirement ID | Description (short) | Story Points | Priority No. | Sprint No. | Assignee | Status
1 | Setup Github | 1 | 1 | 1 | Kiara |  |  | Priority
2 | Setup Python Environment | 1 | 1 | 1 | All |  |  | 1 | High
3 | Create UI Draft (physical) | 2 | 2 | 1 | All |  |  | 2 | Medium
4 | Research: Databases, Hosting, Libraries, etc. | 5 | 1 | 1 | All |  |  | 3 | Low
5 | Create Initial Architecture Document | 3 | 1 | 1 | Reeny | Complete
6 | Decide MVP | 3 | 1 | 1 | All
7 | Develop initial questionnaire | 2 | 2 | 1 | Hart
9 | Implement calendar import/export | 5 | 1 | 1 | Kiara
16 | Create sample data | 2 | 1 | 1 | Reeny | Complete
18 | Create reference stories | 2 | 1 | 1
25 | Setup website | 5 | 1 | 1
43 | Create UI UML Diagram | 5 | 1 | 1 | Ella
44 | Create Import/Export UML Diagram | 5 | 1 | 1 | Audrey
45 | Create UML State Diagram | 5 | 1 | 1 | Lauren
46 | Architecture summary | 2 | 1 | 1 | Hart
8 | Set up data storage | 5 | 1 | 2 |  |  | PostgreSQL for ICS files, map accounts to calendars, better for repeated queries; only have to parse the ics file once; merge calendars | Throw preferences in the SQL database too, map to the user
10 | Create preferences (toggle?) | 3 | 2 | 2
11 | Initial calendar space fill | 3 | 1 | 2
15 | Set up table of event categories | 2 | 2 | 2
17 | Existing Event Parsing (ex, already studying some?) | 5 | 2 | 2
23 | Create SQL inquiries | 3 | 2 | 2
24 | Link file storage | 2 | 2 | 2
28 | Error logging & crash reporting | 2 | 2 | 2
30 | Timezone & DST handling | 2 | 2 | 2
31 | Edge Cases: overlapping events & recurring exceptions | 3 | 2 | 2
37 | Add "Add Task" button + form | 2 | 2 | 2
39 | Display event list under calendar | 2 | 3 | 2
12 | Event Title/Status Fields | 3 | 2 | 3
13 | Recurring Event Selection | 3 | 2 | 3
14 | Recap Questionaires (did they like the study times?) | 2 | 3 | 3
20 | Toggle Between Day -> Week -> Month | 5 | 3 | 3 | Kiara
21 | Recalculate event times | 3 | 3 | 3
26 | Auto-reschedule on conflicts or missed sessions | 5 | 3 | 3
27 | Reminder/Notification service (15 mins before, snooze) | 5 | 2 | 3
29 | Focus Mode (hide non-study events for clean view) | 2 | 3 | 3 | Kiara
32 | Category Color-Coding & Study-Types Legend | 2 | 3 | 3 | Kiara
33 | "Reschedule All" Tool | 3 | 3 | 3
34 | Priority Weights (exam > project > hw?) | 3 | 2 | 3
35 | Undo/Redo History for Schedule Edits | 3 | 2 | 3
36 | Questionnaire-driven personalization | 5 | 3 | 3
38 | Build user login + logout (basic auth?) | 3 | 2 | 3
40 | Track study completion stats | 3 | 3 | 3
41 | Monthy Overview Heatmap (average study hours) | 5 | 3 | 3
42 | Delete Event | 2 | 3 | 3
19 | Create Native Calendar UI | 8 | 3 | 2025-02-03 | Kiara
22 | Testing features | 5 | 3 | 1,2,3
47 | Artifacts Document | 5 | 2 | 2,3
48 | Event Form Removal | 1 | 1 | 3
49 | DB helper class | 5 | 1 | 3
50 | Import file pipelline | 3 | 1 | 3
51 | Expand DB | 2 | 1 | 3
52 | Create Video/Presentation | 5 | 1 | 4

## Sprint 1 Arifacts
Requirement ID | Task Name | Story Points | Priority No. | Sprint No. | Description (long) | Status | Name | Time Estimate
1 | Setup Github | 1 | 1 | 1 | Setup Github repository and add all collaborators | Complete | Kiara | 10 sec
2 | Setup Python Environment | 1 | 1 | 1 | Install initial libraries for project | Complete | All | 1 hr
3 | Create UI Draft (physical) | 2 | 2 | 1 | Create a rough physical diagram of the app flow from the User's perspective | Complete | All | 20 mins
4 | Research: Databases, Hosting, Libraries, etc. | 5 | 1 | 1 | Research various Python libraries and frameworks to look for efficient ways to implement the app. | Complete | All | 2 hrs
5 | Create Initial Architecture Document (except diagrams & descriptions) | 3 | 1 | 1 | Initial draft complete, synopsis done, other reqs done except for architecture description and diagrams | Complete | Reeny | 15 mins
6 | Decide MVP | 3 | 1 | 1 | Define minimum requirements for a working application. | Complete | All | 30 mins
7 | Develop initial questionnaire | 2 | 2 | 1 | Create questions list used to initialize user preferences. | Complete | Hart & Audrey | 15 min
9 | Implement calendar import/export | 5 | 1 | 2 | Create a baseline program that is able to import an ics file and export an ics file. | Complete | Kiara | 2 hrs
16 | Create sample data | 2 | 1 | 1 | created 3 sample ics files we can work with | Complete | Reeny | 30 mins
18 | Create reference stories | 2 | 1 | 1 | Define reference stories for story points. | Complete | All | 2 hrs
22 | Testing features | 5 | 3 | 1 | Test features throughout the project. | In Progress | All | Ongoing
25 | Setup website | 5 | 1 | 2025-01-02 | Create a skeleton web application using Django. Note: to be completed early in sprint 2. | Complete | Kiara | 3 hrs
43 | Create UI UML Diagram | 5 | 1 | 1 | Created UML diagram illustrating the general user flow of how the application will operate | Complete | Ella | 2 hrs
44 | Create Import/Export UML Diagram | 5 | 1 | 1 | Create a UML diagram detailing the program flow for importing and exporting a file. | Complete | Audrey | 1.5 hrs
45 | Create UML State Diagram | 5 | 1 | 1 | Create a UML state diagram that describes how the state of the website changes based on various user inputs. | Complete | Lauren | 2 hrs
46 | Architecture summary | 2 | 1 | 1 | Summarize front-end, back-end, and data flow of the application. Include technologies used, crucial connections between front-end and back-end, and give reader a comprehensive view of how program works. | Complete | Hart | 1.5 hrs

## Sprint 2 Artifacts
Requirement ID | Task Name | Story Points | Priority No. | Sprint No. | Description (long) | Status | Name | Time Estimate
25 | Setup website | 5 | 1 | 2025-01-02 | Create a skeleton web application using Django. Add additional functionality and views, dynamic web pages, etc. to improve user experience. | Complete | Kiara | 4 hrs
37 | Add "Add Task" button + form | 2 | 1 | 2 | Let the user add tasks with various data fields for the application to then add to their calendar. | Complete | Ella | 4 hrs
11 | Initial calendar space fill | 3 | 1 | 2 | Given a calendar and tasks to add, add events in open time slots. | Complete | Hart | 8 hrs |  | How to process calendar? Ella & Kiara agree on format of new events
10 | Create preferences (toggle?) | 3 | 2 | 2 | Define initial preference list to be used to filter and improve schedule suggestions, allowing users to set their preferences. | Complete | Audrey | 3.5 hrs
8 | Set up data storage | 8 | 1 | 2 | Implement data storage using either a database (SQL) or web storage (cookies), to allow for storing user preferences. | Complete | Reeny | 4 hrs
15 | Set up table of event categories | 2 | 2 | 2 | Add event categories for cleaner labeling of events, and to further enhance interactions with preferences. | Complete | Reeny | 1 hr
17 | Existing Event Parsing | 5 | 2 | 2 | Implement scanning of imported calendar for existing events, factoring those into the schedule recommendations. | Complete | Lauren | 3 hrs
28 | Error logging & crash reporting | 2 | 2 | 2 | Handle errors and application crashes in order to help with debugging. | Complete | Audrey | 1 hr
30 | Timezone, time of day handling | 2 | 2 | 2 | Adjust times to handle adding only at reasonable/preferred hours of the day. | Complete | Kiara | Consumed by req 36
31 | Recurring events | 3 | 2 | 2 | Implement adding recurring events that get added to the calendar on multiple days, at the same time or different times. | In Progress | Hart | 0.5 hrs
39 | Display event list under calendar | 2 | 3 | 2025-02-03 | Add UI features to show what events are added to their calendar, and any other information they may want to see. | Complete | Kiara | 2 hrs
19 | Create Native Calendar UI | 8 | 3 | 2025-02-03 | Develop a calendar view so users can see their calendar in-app, with the events added as needed. | In Progress | Kiara | 5 hrs | Rollover
22 | Testing features | 5 | 3 | 1,2,3 | Test features throughout the project | In Progress | All | Many hrs
47 | Artifacts Document (Sprint 1 & 2) | 5 | 2 | 2 | should make stories and description: things to include is already listed in document | Complete | Ella | 1.5 hrs |  | Longer description- more bullet points

## Sprint 3 Artifacts
Requirement ID | Task Name | Story Points | Priority No. | Sprint No. | Description (long) | Status | Name | Time Estimate
12 | Edit Event Title/Status Fields | 3 | 2 | 3 | Let the user edit the event's title, details, and/or status | Not Started | Lauren
14 | Recap Questionaires (did they like the study times?) | 2 | 3 | 3 | At the end of a certain time period (1-2 weeks?), the user will be prompted with a recap questionnaire to update their preferences | Complete | Audrey | 120 min
20 | Toggle Between Day -> Week -> Month | 5 | 3 | 3 | Allow the user to toggle the calendar view to view either a daily, weekly, or monthly schedule | Complete | Kiara
21 | Recalculate event times | 3 | 3 | 3 | After the user is presented with an initial event time, allow the user to reschedule that particular event | In Progress | Hart
26 | Auto-reschedule on conflicts or missed sessions | 3 | 3 | 3 | If the user marks their session as having had a conflict or being missed, the calendar will reschedule that time slot elsewhere | Not Started | Hart
27 | Reminder/Notification service (15 mins before, snooze) | 8+ | 4 | 3 | Develop an "alarm" system that alerts the user when a session/event is about to begin (15 minutes, or customizable). Allow the user to snooze this notification | Not Started | Delay
29 | Focus Mode (hide non-study events for clean view) | 2 | 3 | 3 | Create a toggle on the calendar that will let the user only see certain types of events (i.e., hiding non-study events) | Complete | Kiara | Complete as not doing, fullcalendar broke their filter system
32 | Category Color-Coding & Study-Types Legend | 2 | 3 | 3 | On the Calendar View, color code events by type, with a legend for enhanced readability at a glance | Complete | Kiara
33 | "Reschedule All" Tool | 3 | 3 | 3 | After the user is presented with an initial schedule, allow the user to completely re-randomize a new schedule | In Progress | Hart
34 | Priority Weights (exam > project > hw?) | 3 | 2 | 3 | Create different kinds of events or detail of an event that allows the user to "prioritize" certain events, meaning that they will be scheduled first | Complete | Ella | 30 mins
35 | Undo/Redo History for Schedule Edits | 3 | 2 | 3 | Store the user's edits to the initial schedule so that they can undo/redo their changes | Complete | Ella | 1.5 hr
36 | Questionnaire-driven personalization | 5 | 3 | 3 | If the user has filled out a personal questionnaire of their scheduling preferences, the scheduling algorithm will reference the preferences first before randomizing | Complete | Lauren
38 | Build user login + logout (basic auth?) | 5 | 2 | 3 | Implement a login/authentication flow to link app users to stored calendars and prevent access to others' calendars, as well as track preferences and other data. | Complete | Reeny
40 | Track study completion stats | 3 | 3 | 3 | Design a web page to display basic statistics for event analysis, initially focused on event-type time spent, with an extensible design for additional stats as they become available. | Complete | Audrey | 90 min
41 | Monthy Overview Heatmap (average study hours) | 5 | 3 | 3 | Create a color-coded calendar view where the user can see their average study stats in a graphical display. | In Progress | Audrey
42 | Delete Event | 2 | 3 | 3 | Allow the user to delete an event from their generated schedule | Complete | Ella | 30 mins
19 | Create Native Calendar UI | 8 | 3 | 2025-02-03 | Develop a calendar view so users can see their calendar in-app, with the events added as needed. | Complete | Kiara
22 | Testing features | 5 | 3 | 1,2,3 | (Recurring Requirement) Test features throughout the project | In Progress | All
47 | Artifacts Document | 5 | 2 | 2,3 | (Recurring Requirement) Create document that details requirements of current and final sprint | Complete | Ella | 1 hr
48 | Event Form Removal | 1 | 1 | 3 | Adjust form removal handling to properly account for event deletion from the Add Events page. | Complete | Ella | 30 mins
49 | DB Helper Class | 5 | 1 | 3 | create a helper class with functions that help accessing our db, minimum includes: adding, retrieving, and deleting data | Complete | Reeny | look into django models, it might do this for us if we set those up properly
50 | Import file pipelline | 3 | 1 | 3 | Import file pipeline: User upload an ics file | In Progress | Kiara | Rollover, stupid math midterm.
51 | Expand DB | 2 | 1 | 3 | make tables: all events, users, preferences | Complete | Reeny
31 | Recurring events | 3 | 2 | 2025-02-03 | Implement adding recurring events that get added to the calendar on multiple days, at the same time or different times. | Complete | Hart | 5 hrs
| Add categories to db to match ui | 1 | 1 | 3 | see ui | Complete | Reeny

## Final Sprint Artifacts
Requirement ID | Task Name | Story Points | Priority No. | Sprint No. | Description (long) | Status | Name | Time Estimate
12 | Edit Event Title/Status Fields | 3 | 2 | 3 | Let the user edit the event's title, details, and/or status | Not Started | Lauren
21 | Recalculate event times | 3 | 3 | 3 | After the user is presented with an initial event time, allow the user to reschedule that particular event | Not Started | Hart
26 | Auto-reschedule on conflicts or missed sessions | 3 | 3 | 3 | If the user marks their session as having had a conflict or being missed, the calendar will reschedule that time slot elsewhere | Not Started | Hart
27 | Reminder/Notification service (15 mins before, snooze) | 8+ | 4 | 3 | Develop an "alarm" system that alerts the user when a session/event is about to begin (15 minutes, or customizable). Allow the user to snooze this notification | Not Started | Delay
29 | Focus Mode (hide non-study events for clean view) | 2 | 3 | 3 | Create a toggle on the calendar that will let the user only see certain types of events (i.e., hiding non-study events) | Not Started | Kiara
32 | Category Color-Coding & Study-Types Legend | 2 | 3 | 3 | On the Calendar View, color code events by type, with a legend for enhanced readability at a glance. Allow users to set colors for different types of events. | In Progress | Kiara
33 | "Reschedule All" Tool | 3 | 3 | 3 | After the user is presented with an initial schedule, allow the user to completely re-randomize a new schedule | Not Started | Hart
36 | Questionnaire-driven personalization | 5 | 3 | 3 | If the user has filled out a personal questionnaire of their scheduling preferences, the scheduling algorithm will reference the preferences first before randomizing | Not Started | Lauren
38 | Build user login + logout (basic auth?) | 5 | 2 | 3 | Implement a login/authentication flow to link app users to stored calendars and prevent access to others' calendars, as well as track preferences and other data. | Not Started | Reeny
41 | Monthy Overview Heatmap (average study hours) | 5 | 3 | 3 | Create a color-coded calendar view where the user can see their average study stats in a graphical display. | Not Started | Audrey
22 | Testing features | 5 | 3 | 1,2,3 | (Recurring Requirement) Test features throughout the project | In Progress | All
50 | Import file pipelline | 3 | 1 | 3 | Import file pipeline: User upload an ics file | In Progress | Kiara